## Sheet1
Reflection on Iteration #2
Context Project: Bubble Trouble
Group Number: 4
User Story | Task # | Task | Assignee | Relative Estimated Effort | Actual Effort | Done | Notes
1. Refactoring As a developer I want to have a clean code base, so I can easily maintain and extend the code | 1 | Create subclasses for each bubble type | Casper | 0.5 | 0.5 | Yes | -
| 2 | Create subclasses for each pickup type | Casper | 0.5 | 0.5 | Yes | -
| 3 | Create subclasses for each weapon type | Casper | 0.5 | 0.5 | Yes | -
| 4 | Refactor the pickup package to make each pickup handle their own effects. (This includes removal of the PickupContent class) | Casper | 1.5 | 1.5 | Yes | -
| 5 | Refactor the update method of Game to decrease method length and use of the Quadtree | Damian | 0.5 | 0.5 | Yes | -
| 6 | Weapon must have an instance of Player in the constructor signature to enforce a composition relationship. | Casper | 0.25 | 0 | No | Not beneficial with the current pick-up structure. Also would take much more time than initially expected.
| 7 | Wrap the resources class in an instantiatable class, to allow the testers to mock this object and therefore be able to run tests on Travis | Wouter | 0.5 | 2 | Yes | Required a lot of change throughout the code, took a lot of effort.
| 8 | Enable the possibility to initialize players on a certain spot at the start of a level | Wouter | 0.5 | 0 | No | Skipped because of time constraints and low priority.
| 9 | Add useful JavaDoc (with tags and hyperlinks) to all methods and classes. | All | 0.25 | 0.25 | Yes | Not a separate task, but it was executed.
| 10 | Reduce all method lengths to at most 30 lines | All | 0.25 | 0.25 | Yes | Not a separate task, but it was executed.
| 11 | Reduce the responsibilities of the Player class | Wouter | 0.75 | 0.75 | Yes | Done by Casper instead.
| 12 | Refactor GameState | Justin | 0.5 | 0 | No | Skipped because of time constraints and low priority.
| 13 | Write tests for existing code | All | 0.5 | 2 | Yes | Tests took more time than expected. Done by Casper in particular.
| 14 | Make the tests work on Travis | Justin | 0.5 | 1.5 | Yes | Done by Wouter.
2. Shop Implementation As a user, I want to be able to buy items in a shop, so that I can enhance my gaming experience | 1 | Make shop interface | Damian | 1 | 2.5 | Yes | Took longer than expected because of unclear code specifications.
| 2 | Make Shop GameState to switch to | Damian | 0.25 | 0.25 | Yes | Very small task, could have been part of the task #1.
| 3 | Create UML for shop item structure. | Wouter | 0.25 | 0.5 | Yes | -
| 4 | Create Money | Bram | 0.75 | 1 | Yes | -
| 5 | Create level-centric shop items | Bram | 0.75 | 1 | Yes | -
| 6 | Create player-centric shop items | Bram | 0.75 | 1 | Yes | -
| 7 | Add money to the dashboard | Justin | 0.5 | 0.75 | Yes | -
Total |  |  |  | 11.75 | 16.25
Main Problems Encountered
Problem 1 | Description | Strict deadlines for other subjects. We lost a full day because of the other deadline.
| Reaction | We did most of the work on the last day. This was not a good reaction and the result was that the implemented code still had obvious bugs. These bugs were fixed within 24 hours after the deadline.
Problem 2 | Description | Underestimation of the relative effort.
| Reaction | We worked more hours to finish the most important tasks and skipped some small and unnecessary refactoring tasks. These tasks would not have had direct impact on the maintainability and extendability of the code base.
Adjustments for the next iteration
Better distributed task assignment | In the next iteration, we will focus on even stricter task assignment. Specifically, we will make sure to distribute the high priority tasks evenly, so that every collaborator will be working on the things that matter. Before, we had certain collaborators that were working on low prioritiy tasks, while higher priority tasks were not fully completed (such as remaining bugs in the shop).
Better planning of other overlapping deadlines | In the future, when other deadlines overlap with the sprint deadline and sprint period, we will make sure to complete these other deadlines earlier, preferably even before the sprint starts. This will reduce stress on the already high-paced sprints.
Improving assignment documentation | Retrospectively, we forgot to document our design choices and process. This made grading our work hard for the TA, and caused some confusion during the implementation process. In future iterations, we will make sure to clearly document our changes with both UML and natural languages.